## Gantt Chart
Project proposal title:
Acronym:
Principal Investigator (PI):
Description Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Work Package 1
Subactivity 1.1
Subactivity 1.2
Subactivity 1.3
Work Package 2
Subactivity 2.1
Subactivity 2.2
Subactivity 2.3
Subactivity 2.4
Subactivity 2.5
Work Package 3
Subactivity 3.1
Subactivity 3.2
Subactivity 3.3
Subactivity 3.4
Work Package 4
Subactivity 4.1
Milestones and Deliverables
Milestone and Deliverables 1
Milestone and Deliverables 2
Milestone and Deliverables 3
Milestone and Deliverables 4
Final Report
Participants (% of working time)* | [36 empty] | Effective person-months
Principal investigator (PI) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Participant 1 (P1) |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.5
Participant 2 (P2) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 36
Participant 3 (P3) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | [9 empty] | 30 | 30 | 30 | [7 empty] | 20 | 25 | 5.85
Participant 4 (P4) | [12 empty] | 10 | 10 | 10 | 10 | 10 | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [5 empty] | 10 | 10 | 1.4
Participant 5 (P5) | [5 empty] | 5 | [9 empty] | 5 | 5 | [5 empty] | 5 | 5 |  |  |  | 5 | 5 | [5 empty] | 5 | 5 | 0.45
Total effective person-months | [36 empty] | 65
*In case that the project proposal involve participant from Diaspora and/or retired university professor/retired principal research fellow/professor emeritus/retired member of the Serbian Academy of Sciences and Arts please note that this participant should be presented in the Gantt Chart in all segments as other participants, including % of working time dedicated to the project.